## Overall Summary
Random Date Generator (RDG) | [5 empty] | 2020-05-17
| PI | 2
| Sprint | 3 | Execution Summary |  |  |  | Pass % | 23.08%
| Sprint Cycle | 14-Mar to 27-Mar | Stories | TC Coverage | Pass | Fail | Blocked | Deferred | Pending
| Overall Status | Amber | 4 | 13 | 3 | 10 | 0 | 0 | 0
Progress Summary this Cycle
RDG testing is in-progress on Stage environment Test case design has been completed for all in-sprint stories Testing on Chrome browser - Completed Yet to start testing on FF, Safari and IE browsers Automation candidates have been identified and scripting is in progress: 27% completed Initial automation focus is on Chrome browser alone
|  |  | Automation Coverage |  |  |  |  | 18.18%
|  |  | Automation Candidates |  | Cannot Be Automated |  | Automated Tests |  | Pending TCs for Automation
|  |  | 11 |  | 0 |  | 2 |  | 8
Issues & Risks
| Too many defects were uncovered while testing on Chrome - 10 open defects : 4-P1, 3-P2, 3-P3 QA Pass % on chrome browser : 23% |  | Defects Trend |  | P0 | P1 | P2 | P3
|  |  | Open |  | 0 | 4 | 3 | 3 | 10
|  |  | Closed |  | 0 | 0 | 0 | 0 | 0
|  |  | Re-opened |  | 0 | 0 | 0 | 0 | 0
Green
Amber
Red
N/A

## TestCase Coverage
RANDOM DATE GENERATOR (RDG)
Coverage | 100% | [6 empty] | Automation Coverage |  | 18.18%
Stories | TC Coverage | Pass | Fail | Blocked | Deferred | In Progress | Pending | Automation Candidates | Cannot Be Automated | Automated Tests | Pending TCs for Automation
RDG-01 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 5 | 0 | 2 | 2
RDG-02 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
RDG-03 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
RDG-04 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 13 | 3 | 10 | 0 | 0 | 0 | 0 | 11 | 0 | 2 | 8
Story | Test Case ID | Test Case ID | [5 empty] | Status | Defects | Identified for Automation | Automated
RDG-01 | TC-01 | Verify the UI layout of RDG form | [5 empty] | Pass |  | Yes | Automated
RDG-01 | TC-02 | Verify user is able to generate random dates -> in pre-defined output format | [5 empty] | Fail | DEF-03 | Yes | In Progress
RDG-01 | TC-03 | Verify user is able to generate random dates -> in custom date format | [5 empty] | Fail | DEF-05 | Yes | Yet To Automate
RDG-01 | TC-04 | Verify dates are not generated when anyone one of the input field is empty | [5 empty] | Pass |  | Yes | Yet To Automate
RDG-02 | TC-05 | Check field level validation for "How many dates to generate?" | [5 empty] | Fail | DEF-07 | Yes | Yet To Automate
RDG-02 | TC-06 | Check field level validation for "Custom date format" | [5 empty] | Fail | DEF-06 | Yes | Yet To Automate
RDG-02 | TC-07 | Check field level validation for "Start Date" | [5 empty] | Fail | DEF-08 | Yes | Yet To Automate
RDG-02 | TC-08 | Check field level validation for End Date" | [5 empty] | Fail | DEF-09 | Yes | Yet To Automate
RDG-03 | TC-09 | Verify user is able to add "Random Date Generator to favorites" | [5 empty] | Fail | DEF-01 | Yes | Yet To Automate
RDG-03 | TC-10 | Verify user is able to save and share the generated random dates | [5 empty] | Fail | DEF-10 | Yes | Yet To Automate
RDG-01 | TC-11 | Verify user is able to generate NEW random dates every time the RDG button is clicked | [5 empty] | Pass |  | Yes | Automated
RDG-04 | TC-12 | Verify dates are not generated unless the RDG button is clicked | [5 empty] | Fail | DEF-02 | No
RDG-04 | TC-13 | Verify generated date format is changing while changing the pre-defined date format | [5 empty] | Fail | DEF-04 | No

## Test Cases
Story | TestCase ID | Test Summary | Test Steps | Input Data | Expected Results | Status | Defects
RDG-01 | TC-01 | Verify the UI layout of RDG form | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Verify the following fields are present in the form:- - RDG - add to favorite - Save & Share button - Generate Random Dates button - Output Test Area - Inputbox: Number of dates - Dropdown: Data output format - Inputbox: Custom date format - Inputbox: Start date & End date - Labels for all the above fields |  | 1. RDG site is accessible 2. Following fields should be present in the form:- - RDG - add to favorite - Save & Share button - Generate Random Dates button - Output Test Area - Inputbox: Number of dates - Dropdown: Data output format - Inputbox: Custom date format - Inputbox: Start date & End date - Labels for all the above fields | Pass
RDG-01 | TC-02 | Verify user is able to generate random dates -> in pre-defined output format | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Enter no. of dates 3. Select output format 4. Enter Start date & End date 5 Click on 'Generate Random Dates' 6. Verify the date is generated in selected output date format 7. Verify generated date is within the defined range 8. Test the above scenarios for all the predefined output format | # date Count: <<2>> # date output format: YYYY-MM-DD hh:mm:ss YYYY-DD-MM hh:mm:ss MM-DD-YYYY hh:mm:ss ISO 8601 Year Month Date hh:mm:ss Year Date Month hh:mm:ss Month Date Year hh:mm:ss #start date: 2020 #end date: 2021 | ams 3. <<2>> random dates are generated in output text area based on the selected output date format 4. Generated dates should be within the defined start & end dates | Fail | DEF-03
RDG-01 | TC-03 | Verify user is able to generate random dates -> in custom date format | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Enter no. of dates 3. Select output format as 'Custom date format' 4. Enter custom date format 5. Enter Start date & End date 6 Click on 'Generate Random Dates' 7. Verify the date is generated in custom date format entered 8. Verify generated date is within the defined range 9. Test the above scenarios for all custom data mentioned in 'Input data' column | # date Count: <<3>> # date output format: Custom date format # custom date format: YYYY MM DD YYYY-month-DD YYYY mon d YY-MM-D hh mm ss YY MM D h m s YY-mon-DD hh m s #start date: 2020 #end date: 2021 | 1. RDG site is accessible 2. User is able to enter data in all the fields 3. <<3>> random dates are generated in output text area based on the custom date format entered 4. Generated dates should be within the defined start & end dates | Fail | DEF-05
RDG-01 | TC-04 | Verify dates are not generated when anyone one of the input field is empty | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Do not provide any input and click on random date generator 3. Enter no. of dates as 2 and click on random date generator 4. Enter Start date and click on random date generator 5. Enter End date but clear Start date and click on random date generator |  | 1. RDG site is accessible 2. No date is generated 3. No date is generated 4. No date is generated 5. No date is generated | Pass
RDG-02 | TC-05 | Check field level validation for "How many dates to generate?" | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Enter invalid data in No. of dates field as mentioned in 'Input data' 3. Enter valid data in rest of the fields 4. Click on Random date generator button 5. Test the above scenarios for all invalid data mentioned in 'Input data' column | #No. of dates alphabets 9999999 leave as blank special chars | 1. RDG site is accessible 2. Error message should be displayed to the user "Invalid data" for field - "How many dates to generate?" | Fail | DEF-07
RDG-02 | TC-06 | Check field level validation for "Custom date format" | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Select output data format as Custom and enter invalid data in custom date format field as mentioned in 'input data' 3. Enter valid data in rest of the fields 4. Click on Random date generator button 5. Test the above scenarios for all invalid data mentioned in 'Input data' column | #No. of dates alphabets 9999999 leave as blank special chars | 1. RDG site is accessible 2. Error message should be displayed to the user "Invalid data" for field - "Custom date format" | Fail | DEF-06
RDG-02 | TC-07 | Check field level validation for "Start Date" | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Enter invalid data in Start Date field as mentioned in 'Input data' 3. Enter valid data in rest of the fields 4. Click on Random date generator button 5. Test the above scenarios for all invalid data mentioned in 'Input data' column | #No. of dates alphabets 9999999 leave as blank special chars | 1. RDG site is accessible 2. Error message should be displayed to the user "Invalid data" for field - "Start date" | Fail | DEF-08
RDG-02 | TC-08 | Check field level validation for End Date" | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Enter invalid data in End Date field as mentioned in 'Input data' 3. Enter valid data in rest of the fields 4. Click on Random date generator button 5. Test the above scenarios for all invalid data mentioned in 'Input data' column | #No. of dates alphabets 9999999 leave as blank special chars | 1. RDG site is accessible 2. Error message should be displayed to the user "Invalid data" for field - "End date" | Fail | DEF-09
RDG-03 | TC-09 | Verify user is able to add "Random Date Generator to favorites" | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Click * next to random date generator page title in the top-left 3. verify the site is added to favorites |  | 1. RDG site is accessible 2. * color should get changed to <<green>> 3. Site should be added to favorites | Fail | DEF-01
RDG-03 | TC-10 | Verify user is able to save and share the generated random dates | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Enter valid data in all the field and generate random dates 3. Click on 'Save& Share' button |  | 1. RDG site is accessible 2. Random dates are generated 3. User is provided an option to save and share the generated dates | Fail | DEF-10
RDG-01 | TC-11 | Verify user is able to generate NEW random dates every time the RDG button is clicked | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Enter no. of dates between <<1-5>> 3. Select any output date format 4. Enter Start date & End date 5 Click on 'Generate Random Dates' 6. Verify random dates are generated in output text area 7 Click on 'Generate Random Dates' again, multiple times 8. Verify NEW random dates are generated in output text area |  | 1. RDG site is accessible 2. User is able to enter data in all the fields 3. Clicking on Random Date Generator button displays <<1-5>> random dates in the output text area 4. Clicking again on Random Date Generator button everytime, should display NEW <<1-5>> random dates in the output text area | Pass
RDG-04 | TC-12 | Verify dates are not generated unless the RDG button is clicked | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Enter any no. of dates 3. Select any output date format 4. Enter Start date & End date 5 Click anywhere on the screen |  | 1. RDG site is accessible 2. User is able to enter data in all the fields 3. Dates should not be generated in the Output text area when user enters the No. of dates 4. Dates should not change in the Output text area when user clicks anywhere on the page | Fail | DEF-02
RDG-04 | TC-13 | Verify generated date format is changing while changing the pre-defined date format | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Enter any no. of dates 3. Select any output date format 4. Enter Start date & End date 5. Click on RDG button 6. Change the output date format |  | 1. RDG site is accessible 2. User is able to enter data in all the fields 3. Dates should not be generated in the Output text based on the selected output date format 4. On changing the Output date format, the respective format should get updated in the Output text area | Fail | DEF-04

## Defects
Defect ID | Defect Summary | Steps to Reproduce | Expected Results | Actual Results | Testcase Mapping | Defect Priority | Status
DEF-01 | User is not able to add "Random Date Generator to favorites" | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Click * next to random date generator page title in the top-left 3. verify the site is added to favorites | RDG Site should be added to favorites | RDG Site is NOT added to favorites | TC-09 | P1 | Open
DEF-02 | Dates are generated without clicking on RDG button | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Enter any no. of dates 3. Click anywhere on the screen | 1. Dates should not be generated in the Output text area when user enters the No. of dates 2. Dates should not change in the Output text area when user clicks anywhere on the page | 1. Dates are generated in the Output text area when user enters the No. of dates 2. Dates are changing in the Output text area when user clicks anywhere on the page | TC-12 | P2 | Open
DEF-03 | Mismatch in generated output date format | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Enter any no. of dates 3. Select output date format as " Year Date Month hh:mm:ss " 4. Enter Start date & End date 5 Click on 'Generate Random Dates' 6. Verify the date is generated in selected output date format | Random dates are generated in output text area in the format : " Year Date Month hh:mm:ss " | Random date is generated in in format of : " Year Month Date hh:mm:ss " | TC-02 | P1 | Open
DEF-04 | New date is generated on changing pre-defined output date format | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Enter any no. of dates 3. Select any output date format 4. Enter Start date & End date 5. Click on RDG button 6. Change the output date format | On changing the Output date format, the respective format should get updated in the Output text area | New date is generated on changing output date format | TC-14 | P2 | Open
DEF-05 | Generated dates contains numerical values in month name - > custom date format | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Enter no. of dates 3. Select output format as 'Custom date format' 4. Enter custom date format : "YYYY-month-DD" 5. Enter Start date & End date 6 Click on 'Generate Random Dates' | Random dates are generated in output text area in the format : "YYYY-month-DD" | Numerical values are appearing in month name: e.g. "2020-Augu15t-30" | TC-03 | P2 | Open
DEF-06 | No field level validation for "Custom date format" field | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Select output data format as Custom and enter invalid data in custom date format field as :- -> YYYY - M - D -> YYYY - abc123 @# 3. Enter valid data in rest of the fields 4. Click on Random date generator button | Error message should be displayed to user "Invalid data" for field - "Custom date format" and should allow only the following format: YYYY YY MM month mon DD d hh h mm m ss s | No Error message displayed and custom date field accepts all alpha numerical values | TC-06 | P3 | Open
DEF-07 | No upper limit defined for No. of dates field and pages crashes on generating large number of dates | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Enter invalid data in No. of dates field as : -> 9999999 -> special chars -> alphabets -> leave as blank 3. Enter valid data in rest of the fields 4. Click on Random date generator button | Error message should be displayed to the user "Invalid data" on entering invalid date. Filed should allow only numerical values | No Error message displayed and field accepts all alpha numerical values Page is crashing on entering larger numbers: 99999 | TC-05 | P1 | Open
DEF-08 | Check field level validation for "Start Date" | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Enter invalid data in Start Date field as combination of : -> alphanumerical values -> leave as blank -> special chars 3. Enter valid data in rest of the fields 4. Click on Random date generator button | Error message should be displayed to the user "Invalid data" on entering invalid date. Filed should allow only numerical values | No Error message displayed and field accepts all alpha numerical values | TC-07 | P3 | Open
DEF-09 | Check field level validation for "Start Date" | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Enter invalid data in End Date field as combination of : -> alphanumerical values -> leave as blank -> special chars -> enter end date less than start date 3. Enter valid data in rest of the fields 4. Click on Random date generator button | Error message should be displayed to the user "Invalid data" on entering invalid date. Filed should allow only numerical values | No Error message displayed and field accepts all alpha numerical values It allows end date to be less than start date | TC-08 | P3 | Open
DEF-10 | Save and share functionality is not working | 1. Access RDG site "https://codebeautify.org/generate-random-date" 2. Enter valid data in all the field and generate random dates 3. Click on 'Save& Share' button | User should be able to save and share the generated dates | Random pop-up is displayed to user No option is provided to save and share generated dates | TC-10 | P1 | Open